## Slide 1: Foster the Family Adoption Service Center
Lisa Danovich
Audrey Dowell
Hannah Gross
Alexandra Standal

## Slide 2: What do we do?
  Foster the Family assists foster care parents who are interested in the adoption of their foster care adolescents as they move through the complicated and lengthy adoption process by facilitating support groups, holding seminars and distributing educational documents

## Slide 3: Facts
Youth 13-18 are less likely to be adopted than younger children
Adolescents involved with foster care are about 4x more likely to have attempted suicide & 5x more likely to have substance abuse issues
Adolescents who are adopted have higher levels of emotional security, a stronger sense of belonging, and strong feelings of general well-being than those in a long-term foster care situation
(Department of Human Services, 2011)

## Slide 4: Logic Model
Scope:
Foster the Family will increase adoptions of teenage foster youth, ages 13-18, by prospective foster care parents in Washtenaw County
Inputs
Staff
Time
Activities
Evaluate staff requirements and assign roles
Identify stakeholders and develop outreach plan
Outputs
Support groups for prospective parents
Educational webinars/workshops
Funds
Short-term Outcomes
Flyers with tips on how to navigate the foster care  adoption process
Increased knowledge about the adoption process
Make the adoption process more accessible
Research
Equipment
Experts
Engage stakeholders
Develop streamlined adoption process
Develop internal training programs
Run internal trainings
Develop Foster Family Support Program workshops
Long-term Outcomes
Reduced involvement in the juvenile justice system
Increased graduation rates
Improved social adjustment
Higher rates of employment
Decrease fear about the adoption process

## Slide 5: Key Stakeholders
Stakeholder | Role(s) | Issues | Impacts | Engagement Objectives | Engagement Strategies
Washtenaw County Foster Adoption Agency | Champion Project Owner | Improve Life Quality for Foster Teens | Influence Funders/stakeholders Implement program | ~ Increase teen foster parent adoptions. ~ Reduce adoption process time. ~ Provide Educational outreach to Foster parents. ~.Provide foster/ adoption parent support. | ~ Form coalitions among stakeholders. ~ Stakeholder communication plan. ~ Implement stakeholder engagement plan.
Department of Human Services | Funder/Beneficiary/ Influencer | Save taxpayer $$ over time. | ~ Blueprint for national program. ~ Build social capital for foster teens. ~ Political Reelection | ~ Provide funds. ~ Success:>health,< costs, Strong society, taxpayer savings | ~ Milestone Evaluations ~ Communications ~ Market success.
Juvenile Justice and Delinquency Prevention | Beneficiary/Influencer | Foster teens have high involvement in the JJ system. | ~ Decreased crime rates and court and taxpayer costs. ~ Productive lives. | ~ Decreased crime rates. ~ Less crowded courts and workloads. ~ Less cost. | ~ Stakeholder meetings/committees, communication. ~ Market successes.

## Slide 6: Key Stakeholders
Stakeholder | Role(s) | Issues | Impacts | Engagement Objectives | Engagement Strategies
Adolescent Foster Youth | Beneficiary Customer | ~ Foster Youth have no resources/social capital. ~ Uncompleted education, not ready for independent/ professional life. | Lifelong social capital because of family membership. | ~ Higher education, social adjustment and participation ~ Increased mental/physical health, no crime. | Outreach and market. Counseling & support groups. Inclusionary planning.
Foster & Adoptive Parents | Beneficiary and Customer | ~ Lifetime bonding & attachment issues. ~ Dis-incentives to adopt. | ~ Increase Knowledge. ~Increase adoptions. ~Reduce adoption time. ~Counseling/Support Services | ~ Increase adoption knowledge/capacity. ~ Counseling/Support Groups. ~ Inclusionary Planning. | ~ Outreach/market adoption. ~ Provide counseling/support groups. ~ Inclusionary planning.
Birth Parent | Beneficiary & Customer | Emotional conflict over how to best serve/love their children. | ~ No legal responsibility ~ Possible child involvement. | ~ Increase Knowledge. ~ Increase adoptions. ~ Reduce process time. ~ Support/Counseling. | ~ Outreach/market adoption alternative. ~ Counseling/Support Groups. ~ Inclusionary Planning.

## Slide 7: Key Stakeholders
Stakeholder | Role(s) | Issues | Impacts | Engagement Objectives | Engagement Strategies
Adolescent Foster Youth Social Work Caseworkers | Beneficiary and Customer | ~ Overworked ~ Unfulfilled service providers – Conflict with NASW | – Less Burn-out and Drop-out – Increased Expertise – More Career Satisfaction | – Increased knowledge – Increased Adoptions – Reduction paperwork/time –Birth parent support | – Outreach Adoption – Training – Inclusionary Program Development
Adoption Agency Advocacy Organizations | Beneficiaries and Influencers | – Removing Barriers – Timely “last Chance” – Service Provision | More Permanent Families achieving adoption goals | – Increase Knowledge – Increase Adoptions – Reduce Time – Provide Support | – Outreach – Inform/Support Agency – Inclusionary Planning
Community Middle and High Schools | Impactees | – Behavior Problems in class | Positive Behaviors and contributions | Familiarize Counseling Staff | Provide Information
Community Parents | Impactees | Marginalization | Stabilize Children/Families, Community | Destigmatize Foster Child Adoption | Marketing Materials to Normalize Foster Adoptions.

## Slide 8: Schedule of Activities
Chart: 
| Evaluate Staff Requirements and Assign Roles | Hire Consultant | Develop Funding Plan | Identify Stakeholders | Develop Stakeholder Outreach Plan | Engage Stakeholders | Develop Internal Training Program | Run Internal Training | Develop/Schedule Workshops | Develop/Schedule Webinars | Develop/Schedule Support Groups
Start Date | 40910 | 40910 | 40910 | 40910 | 40917 | 40931 | 40924 | 40952 | 40959 | 40959 | 40959
Duration (days) | 14 | 14 | 21 | 14 | 21 | 153 | 21 | 2 | 60 | 60 | 60

## Slide 9: Budget January-June 2012
Expense | Amount
Personnel | $85,000.00
Project Director | $30,000.00
Research/Outreach Coordinator | $20,000.00
Support Group Facilitator (part-time) | $10,000.00
Outside Consultant (part-time) | $3,000.00
Graphic Designer (part-time) | $4,000.00
Project Evaluator (part-time) | $18,000.00
Facilities | $0.00
Equipment | $5,800.00
Supplies (paper, pencils, ink, envelopes, stamps) | $3,000.00
Laptops (4) | $2,800.00
TOTAL | $90,800.00
Notes: Support group facilitator --- approx 8hr/week for 6 months @50.00/hr
Graphic designer – 4 weeks (brochure, webinar, flyer, ed materials)

## Slide 10: Evaluation
Process
  Gantt Chart & Logic Model
    Monitoring and Communicating Rationale
  Internal Training Evaluation
    Pre and Post-tests
    One on one interviewing
  Client Satisfaction Questionnaire
    Adapted from CSQ-8
  Recording Participation and Background Information

## Slide 11: Evaluation Cont.
Outcome
  Webinar Participant Surveys
    Knowledge and Accuracy
  Workshop Participant Focus Groups
    Explore/discuss impact
  Support Group/Workshop Surveys
    Accessibility
  Follow-up Client Assessments
    Number of successful/unsuccessful adoptions
    Role of Foster the Family

## Slide 12: Resources
References:
Michigan Department of Human Services. (2009, May 26). AFCARS Adoption Reporting System-State Ward Finalized Adoptions By Age Groups. In Michigan Department of Human Services. Retrieved November 30, 2011, from http://mi.gov/documents/dhs/DHS-AdoptionsByAgeGroups_283467_7.pdf
Pilowsky, D. J., & Wu, L. (2006, April). Psychiatric symptoms and substance use disorders in a nationally representative sample of American adolescents involved with foster care [Electronic version]. Journal of Adolescent Health, 38(4), 351-358.
Triseliotis, J. (2002). Long-term foster care or adoption? The evidence examined. Child and Family Social Work, 23-33. Retrieved November 30, 2011
U.S. Department of Health and Human Services. (2007). Report To Congress On Barriers & Success Factors In Adoptions From Foster Care: Perspectives Of Families And Staff Supported By The Adoption Opportunities Program. In Children’s Bureau Administration on Children, Youth and Families. Retrieved November 30, 2011, from http://www.acf.hhs.gov/programs/cb/pubs/barriers/index.htm